## Agile Project Plan
YourRoad Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| YourRoad | Anas TAD | 2019-10-12 | 2020-08-09 | 70% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 back end |  | Anas TAD | 2019-10-14 | 2020-09-07 | 329 | In Progress
| model view controller | Spring tool | Lian ALjundi | 2019-10-14 | 2020-09-07 | 329 | In Progress
| database interactions | Spring tool | Basma Dekar | 2019-10-14 | 2020-09-07 | 329 | In Progress
| Sprint 2 front end |  | Anas TAD | 2019-09-16 | 2020-05-01 | 228 | complete
| android design | designing | hany | 15/10/2019 | 30/10/2019 | 15 | complete | it is able to edit at any time
| android design | programing | hany | 2020-01-04 | 2020-01-05 | 30 | complete | can developed any time to add features
Sprint 3
CLICK HERE TO CREATE IN SMARTSHEET